## Gantt Chart
[COMPANY NAME] ¦ PROJECT GANTT CHART — COVER ASSEMBLY NODE A-01
GANTT NO: GNT-A01-001 |  | PROCESS: Cover Sub-Assembly A-01 |  |  | START DATE: [DD-MMM-YYYY] |  |  | DAYS SHOWN: 20
DEPENDENCY TYPE: Sequential → Node B starts on Node A completion | [5 empty] | OWNER: [Name] |  | REV: Rev. 00
SEQ | NODE | TASK / DELIVERABLE | TYPE | OWNER | START (day) | END (day) | DEPENDENCY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | A-01 | Incoming inspection — covers and rivets | Preparation | QA Inspector | 1 | 1 | Start of project | bar: 1
2 | A-01 | Station setup — fixture + machine + die | Setup | Operator L2 | 1 | 1 | Day 1 | bar: 1 to 20
3 | A-01 | Cover sub-assembly production run | Production | Operator L1+L2 | 2 | 5 | After setup complete | bar: 2 to 5
4 | A-01 | In-process quality checks — 100% per piece | Quality | QA Inspector | 2 | 5 | Concurrent with production | bar: 1 to 20
5 | A-01 | Final inspection and logging | Quality | Operator L1 | 2 | 5 | Concurrent with production | bar: 2 to 5
6 | A-01 | SOP + WI + TWI documentation approval | Documentation | Process Owner | 1 | 3 | Parallel — documentation team | bar: 1 to 20
7 | A-01 | Training — operators on SOP/WI/TWI | Training | Supervisor | 1 | 2 | Before production start | bar: 1 to 2
8 | B-01 | [Node B] Frame assembly — SEQUENTIAL START | Production | [Node B Owner] | 6 | 15 | Starts day 6 — after A-01 complete | bar: 1 to 20
9 | PROJECT | Final QC + shipment preparation | Quality | QA Manager | 14 | 16 | After Node B complete | bar: 14 to 16
10 | PROJECT | Document package release | Documentation | Process Owner | 15 | 17 | Final approvals | bar: 1 to 20
LEGEND: | A-01 Node | B-01 Node (sequential) | Production | Quality | Documentation | Training | Setup
NODE LINK: | Node B-01 (Frame Assembly) is a SEQUENTIAL dependency. It cannot start until Node A-01 is complete. Shown as finish-to-start: A-01 ends Day 5 → B-01 starts Day 6.
DRAFT — PENDING APPROVAL — NOT FOR USE